## Guide
Project controls dashboard
How to use
Yellow cells | Inputs. Everything else is a formula; do not overwrite it.
EVM | Earned value: cost and schedule performance and forecasts.
Schedule | Early and late dates, total float, critical flag.
Risk and PERT | Expected monetary value and three-point estimates.
Benefits | NPV, ROI, benefit-cost ratio and payback.
Source | Formulas from a PMP formulas cheat sheet; sample numbers are illustrative, not real project data.

## EVM
Earned value
Enter PV, EV, AC and BAC in the yellow cells (same currency).
Inputs
PV planned value | 100000
EV earned value | 90000
AC actual cost | 110000
BAC budget at completion | 500000
Results
Metric | Value | Reading
CV = EV - AC
SV = EV - PV
CPI = EV / AC
SPI = EV / PV
EAC (a) = BAC / CPI |  | Typical variance continues
EAC (b) = AC + (BAC - EV) / CPI |  | Remaining work at current CPI
ETC (a) = EAC(b) - AC |  | Remaining cost, from EAC (b)
ETC (b) = (BAC - EV) / CPI |  | Same value as ETC (a) when EAC uses CPI
VAC = BAC - EAC(b)
TCPI = (BAC - EV) / (BAC - AC)
BV = BAC - EV |  | Work still to earn

## Schedule
Schedule and float
Enter duration, early start and late start per activity. Dates are in days from project start.
Activity | Duration | ES early start | LS late start | EF = ES + D | TF = LS - ES | Critical?
A | 3 | 0 | 0
B | 5 | 3 | 3
C | 4 | 3 | 5
D | 2 | 8 | 8
E | 6 | 10 | 10
Project duration = max EF
Critical activities

## Risk and PERT
Risk exposure and PERT
Probability as a fraction (0.3 = 30%). Impact in currency.
Risk | Probability | Impact | RE = P x I | Detectability 1-10 | RPN = P x I x D
Supplier delay | 30% | -40000 |  | 4
Scope creep | 50% | -25000 |  | 6
Early delivery bonus | 10% | 30000 |  | 2
EMV = sum of RE
PERT three-point estimate
Task | O optimistic | M most likely | P pessimistic | E = (O+4M+P)/6 | Variance ((P-O)/6)^2 | Std dev
Build module | 10 | 15 | 26
Test | 4 | 6 | 14
Total expected

## Benefits
Benefits: NPV, ROI, BCR, payback
Year 0 is the initial investment (negative). Discount rate as a fraction.
Discount rate r | 8%
Year t | Benefits | Costs | Discounted net
0 | 0 | 200000
1 | 70000 | 10000
2 | 90000 | 10000
3 | 110000 | 10000
4 | 110000 | 10000
NPV
ROI (%) = net benefits / total investment x 100 |  | Undiscounted
BCR = total benefits / total costs
Payback (years) = investment / average annual net benefit |  | Uses the average of years 1 to 4