## Roadmap
Project management road map tracker
Phases and deliverables follow the Template22 Project Management Road Map graphic. Blue cells are inputs: owner, due date, status. Today is read from TODAY(), so overdue flags change daily.
# | Phase | Deliverable | Owner | Due date | Status | Overdue?
1 | Project Initiation | Business case |  | 2026-11-02 | Done
1 | Project Initiation | Project charter |  | 2026-11-03 | Done
1 | Project Initiation | Project assessment |  | 2026-11-04 | Done
1 | Project Initiation | Identify stakeholders |  | 2026-11-05 | Done
1 | Project Initiation | Approval and go/no-go |  | 2026-11-06 | Done
2 | Project Planning | Project management plan |  | 2026-11-09 | In progress
2 | Project Planning | Scope statement |  | 2026-11-10 | In progress
2 | Project Planning | Work breakdown structure (WBS) |  | 2026-11-11 | In progress
2 | Project Planning | Schedule plan |  | 2026-11-12 | Not started
2 | Project Planning | Cost plan |  | 2026-11-13 | Blocked
2 | Project Planning | Resource plan |  | 2026-11-14 | Not started
2 | Project Planning | Risk management plan |  | 2026-11-15 | Not started
2 | Project Planning | Communication plan |  | 2026-11-16 | Not started
3 | Project Scheduling | Activity list |  | 2026-11-16 | Not started
3 | Project Scheduling | Task sequencing |  | 2026-11-17 | Not started
3 | Project Scheduling | Duration estimation |  | 2026-11-18 | Not started
3 | Project Scheduling | Gantt chart |  | 2026-11-19 | Not started
3 | Project Scheduling | Milestone plan |  | 2026-11-20 | Not started
3 | Project Scheduling | Schedule baseline |  | 2026-11-21 | Not started
4 | Resource Management | Resource planning |  | 2026-11-23 | Not started
4 | Resource Management | Resource allocation |  | 2026-11-24 | Not started
4 | Resource Management | RACI matrix |  | 2026-11-25 | Not started
4 | Resource Management | Team development plan |  | 2026-11-26 | Not started
4 | Resource Management | Training plan |  | 2026-11-27 | Not started
4 | Resource Management | Resource tracking |  | 2026-11-28 | Not started
5 | Risk Management | Risk identification |  | 2026-11-30 | Not started
5 | Risk Management | Risk assessment |  | 2026-12-01 | Not started
5 | Risk Management | Risk register |  | 2026-12-02 | Not started
5 | Risk Management | Risk response plan |  | 2026-12-03 | Not started
5 | Risk Management | Risk monitoring |  | 2026-12-04 | Not started
5 | Risk Management | Contingency plan |  | 2026-12-05 | Not started
6 | Procurement Management | Procurement plan |  | 2026-12-07 | Not started
6 | Procurement Management | Make or buy analysis |  | 2026-12-08 | Not started
6 | Procurement Management | Supplier evaluation |  | 2026-12-09 | Not started
6 | Procurement Management | Contract management |  | 2026-12-10 | Not started
6 | Procurement Management | Purchase order |  | 2026-12-11 | Not started
6 | Procurement Management | Procurement tracking |  | 2026-12-12 | Not started
7 | Stakeholder Management | Stakeholder identification |  | 2026-12-14 | Not started
7 | Stakeholder Management | Stakeholder analysis |  | 2026-12-15 | Not started
7 | Stakeholder Management | Engagement plan |  | 2026-12-16 | Not started
7 | Stakeholder Management | Communication plan |  | 2026-12-17 | Not started
7 | Stakeholder Management | Stakeholder register |  | 2026-12-18 | Not started
7 | Stakeholder Management | Feedback management |  | 2026-12-19 | Not started
8 | Quality Management | Quality planning |  | 2026-12-21 | Not started
8 | Quality Management | Quality standards |  | 2026-12-22 | Not started
8 | Quality Management | Quality assurance |  | 2026-12-23 | Not started
8 | Quality Management | Quality control |  | 2026-12-24 | Not started
8 | Quality Management | Inspection checklist |  | 2026-12-25 | Not started
8 | Quality Management | Quality metrics |  | 2026-12-26 | Not started
9 | Project Execution | Task execution |  | 2026-12-28 | Not started
9 | Project Execution | Team collaboration |  | 2026-12-29 | Not started
9 | Project Execution | Deliverable development |  | 2026-12-30 | Not started
9 | Project Execution | Progress monitoring |  | 2026-12-31 | Not started
9 | Project Execution | Issue management |  | 2027-01-01 | Not started
9 | Project Execution | Status reporting |  | 2027-01-02 | Not started
10 | Cost Management | Cost estimation |  | 2027-01-04 | Not started
10 | Cost Management | Budget planning |  | 2027-01-05 | Not started
10 | Cost Management | Cost tracking |  | 2027-01-06 | Not started
10 | Cost Management | Earned value management |  | 2027-01-07 | Not started
10 | Cost Management | Variance analysis |  | 2027-01-08 | Not started
10 | Cost Management | Cost control measures |  | 2027-01-09 | Not started
11 | Change Management | Change request |  | 2027-01-11 | Not started
11 | Change Management | Impact assessment |  | 2027-01-12 | Not started
11 | Change Management | Change log |  | 2027-01-13 | Not started
11 | Change Management | Approval workflow |  | 2027-01-14 | Not started
11 | Change Management | Implementation plan |  | 2027-01-15 | Not started
11 | Change Management | Change monitoring |  | 2027-01-16 | Not started
12 | Monitoring and Controlling | Performance tracking |  | 2027-01-18 | Not started
12 | Monitoring and Controlling | KPI dashboard |  | 2027-01-19 | Not started
12 | Monitoring and Controlling | Variance analysis |  | 2027-01-20 | Not started
12 | Monitoring and Controlling | Risk and issue monitoring |  | 2027-01-21 | Not started
12 | Monitoring and Controlling | Quality monitoring |  | 2027-01-22 | Not started
12 | Monitoring and Controlling | Corrective actions |  | 2027-01-23 | Not started
12 | Monitoring and Controlling | Project reporting |  | 2027-01-24 | Not started
13 | Project Closure | Final deliverables |  | 2027-01-25 | Not started
13 | Project Closure | Project closure report |  | 2027-01-26 | Not started
13 | Project Closure | Lessons learned |  | 2027-01-27 | Not started
13 | Project Closure | Stakeholder sign-off |  | 2027-01-28 | Not started
13 | Project Closure | Release resources |  | 2027-01-29 | Not started
13 | Project Closure | Archive project documents |  | 2027-01-30 | Not started
Formulas:
Overdue? = IF(AND([Due date]<TODAY(),[Status]<>"Done"),"Overdue","")

## Phase summary
Progress by phase
# | Phase | Deliverables | Done | In progress | Blocked | Overdue | % done
1 | Project Initiation | 5 | 5 | 0 | 0 | 0 | 100%
2 | Project Planning | 8 | 0 | 3 | 1 | 0 | 0%
3 | Project Scheduling | 6 | 0 | 0 | 0 | 0 | 0%
4 | Resource Management | 6 | 0 | 0 | 0 | 0 | 0%
5 | Risk Management | 6 | 0 | 0 | 0 | 0 | 0%
6 | Procurement Management | 6 | 0 | 0 | 0 | 0 | 0%
7 | Stakeholder Management | 6 | 0 | 0 | 0 | 0 | 0%
8 | Quality Management | 6 | 0 | 0 | 0 | 0 | 0%
9 | Project Execution | 6 | 0 | 0 | 0 | 0 | 0%
10 | Cost Management | 6 | 0 | 0 | 0 | 0 | 0%
11 | Change Management | 6 | 0 | 0 | 0 | 0 | 0%
12 | Monitoring and Controlling | 7 | 0 | 0 | 0 | 0 | 0%
13 | Project Closure | 6 | 0 | 0 | 0 | 0 | 0%
| All phases | 80 | 5 | 3 | 1 | 0 | 6.25%

## CF practice
Conditional formatting practice: budget versus actual
Inputs in blue. Each rule below is applied to the range named in row 4 of the Notes tab.
Line | Owner | Budget | Actual | Variance | Variance % | Status note | Score
Software | Ana | 12000 | 13800 | 1800 | 15% | Over, needs approval | 72
Travel | Ben | 8000 | 6100 | -1900 | -23.75% | Under | 88
Marketing | Cara | 25000 | 26500 | 1500 | 6% | Over, needs approval | 64
Hosting | Dev | 9000 | 9000 | 0 | 0% | On plan | 91
Training | Ana | 5000 | 2900 | -2100 | -42% | Under | 55
Contractors | Eli | 30000 | 36400 | 6400 | 21.33% | Over, blocked by PO | 48
Legal | Cara | 7000 | 7350 | 350 | 5% | On plan | 79
Office | Ben | 4000 | 3200 | -800 | -20% | Under | 83
Hosting | Dev | 9000 | 9000 | 0 | 0% | Duplicate line | 91
Events | Eli | 15000 | 11800 | -3200 | -21.33% | Under | 60

## Notes
Sheet | What it shows
Roadmap | 80 deliverables across 13 phases; status dropdown; rows turn green when Done and red when Blocked; Overdue? uses TODAY()
Phase summary | COUNTIFS per phase and a data bar for % done
CF practice | Rules applied: variance over 10% (red), duplicate Line (yellow), top 3 Scores (green), text contains "blocked" (red), data bars on Actual, arrow icons on Variance, custom formula on Owner (variance over 10% and score under 60)
Assumptions | Due dates are placeholders from 2 Nov 2026, one week per phase; replace them. Sample statuses are examples, not real progress. Rules are standard Excel conditional formats; the PivotTable features in the pivot infographic cannot be created by this file, so build a pivot from the CF practice table in Excel.